## Untitled
ID | Workstream | Task | Detail / deliverable | Priority | Difficulty | Owner | Support | Start | Due | Duration (days) | Days to due | Depends on | Critical path | Status | Notes / source | Week of → | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12
POST-01 | Project management | Kickoff call, diligence request list, working-group list and calendar | Weekly deal call through signing | P1 - Critical | Low | Frank | Tereno | 2026-10-19 | 2026-10-21 | 3 | 24 | PRE-27 | Y | Not started | bar: 2026-10-19
POST-02 | Diligence | Keystone target data room populated | Financials, contracts, roster, vendor agreements, IP, tax filings | P1 - Critical | Medium | Ben | Frank | 2026-10-19 | 2026-10-30 | 12 | 33 | POST-01 | Y | Not started | bar: 2026-10-19 to 2026-10-26
POST-03 | Tax & structure | Tax structure memo | F-reorg, 99-5 treatment, NH BPT, QSBS opinion on Topkey shares, §83 repurchase, Form 8594 allocation, §754, tax distributions | P1 - Critical | High | Tax counsel | Josh, Frank | 2026-10-19 | 2026-11-13 | 26 | 47 | PRE-03 | Y | Not started | bar: 2026-10-19 to 2026-11-09
POST-04 | Diligence | Entity and tax diligence | Formation docs, S-election acceptance, stock basis/AAA, NH DP-80 apportionment, §174 treatment of Arch/portal | P2 - High | Medium | Tax counsel | Josh | 2026-10-19 | 2026-11-13 | 26 | 47 | POST-02 | N | Not started | bar: 2026-10-19 to 2026-11-09
POST-05 | Financing & consents | Thread payoff executed | Payoff letter, UCC-3 termination, DACA terminations (Mercury, Brex), warrant status | P1 - Critical | Medium | Jon | Josh, Corey | 2026-10-19 | 2026-11-30 | 43 | 64 | PRE-11 | Y | Not started | LSA §2.6 | bar: 2026-10-19 to 2026-11-30
POST-06 | Financing & consents | Charge-card wind-down and reserve release | Collect $779K receivables, release reserve and operational balances, settle $476K reward-points liability | P2 - High | Medium | Josh | Jon | 2026-10-19 | 2026-12-31 | 74 | 95 | POST-05 | N | Not started | Financials 8/31/26 | bar: 2026-10-19 to 2026-12-28
POST-07 | Financing & consents | Insider bridge SAFE closed (if pursued) | Restores runway before closing cash goes out | P2 - High | High | Jon | Josh, Corey | 2026-10-19 | 2026-12-11 | 54 | 75 | PRE-06 | N | Not started | bar: 2026-10-19 to 2026-12-07
POST-08 | Diligence | Reverse diligence by Ben's advisors | Q&A on Topkey package, preference stack, runway | P2 - High | Medium | Ben | Josh, Frank | 2026-10-19 | 2026-11-13 | 26 | 47 | PRE-22 | N | Not started | bar: 2026-10-19 to 2026-11-09
POST-09 | Diligence | Quality of earnings and working-capital peg | Normalized EBITDA ($470–500K), deferred revenue as operating liability, card/revolver balances cleared | P1 - Critical | High | Josh | Frank | 2026-10-26 | 2026-11-20 | 26 | 54 | POST-02 | Y | Not started | bar: 2026-10-26 to 2026-11-16
POST-10 | Diligence | Client contracts, retention and churn | Revenue per client, properties per client, SMB book sale, departures | P2 - High | Medium | Frank | Tereno | 2026-10-26 | 2026-11-13 | 19 | 47 | POST-02 | N | Not started | bar: 2026-10-26 to 2026-11-09
POST-11 | Diligence | Offshore team classification and go-forward model | Philippines counsel view; EOR for client leads and accounting staff; special indemnity scope | P1 - Critical | High | Corey | PH counsel, Ben | 2026-10-26 | 2026-11-25 | 31 | 59 | POST-02 | Y | Not started | LOI 7(d); Options doc Decision 8 | bar: 2026-10-26 to 2026-11-23
POST-12 | Diligence | Vendor and software contract assignability | VR Platform, Karbon (through Apr 2027), other tools | P2 - High | Medium | Frank | Corey | 2026-10-26 | 2026-11-13 | 19 | 47 | POST-02 | N | Not started | bar: 2026-10-26 to 2026-11-09
POST-13 | Diligence | IP assignment confirmation | Arch, client portal, developer work product assigned to Keystone | P2 - High | Medium | Corey | Ben | 2026-10-26 | 2026-11-13 | 19 | 47 | POST-02 | N | Not started | bar: 2026-10-26 to 2026-11-09
POST-14 | Diligence | Franchise, marketplace and referral agreements | PMI, PMS marketplaces, STR Secrets, commissions | P2 - High | Low | Frank |  | 2026-10-26 | 2026-11-13 | 19 | 47 | POST-02 | N | Not started | bar: 2026-10-26 to 2026-11-09
POST-15 | Documents | Membership interest purchase agreement – first draft | Reps, indemnity (10% cap, 0.75% basket, 15 months), escrow, set-off, special indemnity, Topkey reps | P1 - Critical | High | Corey | Frank | 2026-10-26 | 2026-11-13 | 19 | 47 | PRE-27 | Y | Not started | bar: 2026-10-26 to 2026-11-09
POST-16 | Documents | A&R Operating Agreement – first draft | Board, consent rights, tax distributions, ROFR/tag/drag, call (yrs 3–5) and put (yr 5), Formula Price, credit-support limit | P1 - Critical | High | Corey | Frank | 2026-10-26 | 2026-11-13 | 19 | 47 | PRE-27 | Y | Not started | LOI Exhibit A | bar: 2026-10-26 to 2026-11-09
POST-17 | Documents | Services Schedule | Topkey product pricing, engineering support and IP ownership/licence, referral fee | P1 - Critical | Medium | Frank | Jon, Corey | 2026-11-02 | 2026-11-20 | 19 | 54 | POST-16 | N | Not started | LOI 7(b) | bar: 2026-11-02 to 2026-11-16
POST-18 | Integration | Migration Protocol | Readiness criteria, cohort sign-off by Ben, Jan–Feb blackout, trust accounts last; tied to trust-accounting general availability | P2 - High | Medium | Pete | Darren, Ben, Frank | 2026-11-02 | 2026-11-25 | 24 | 59 |  | N | Not started | bar: 2026-11-02 to 2026-11-23
POST-19 | Documents | Ben employment and restrictive-covenant agreements | Title, bonus metrics, severance, Good Reason, non-compete (NH enforceability; Ben abroad) | P1 - Critical | Medium | Corey | Jon | 2026-11-02 | 2026-11-25 | 24 | 59 | PRE-27 | N | Not started | bar: 2026-11-02 to 2026-11-23
POST-20 | Documents | Related-party recruiting agreement | Arm's-length terms; approved in stockholder consent | P3 - Medium | Low | Corey | Ben | 2026-11-16 | 2026-12-04 | 19 | 68 |  | N | Not started | Charter §3.3.8 | bar: 2026-11-16 to 2026-11-30
POST-21 | Tax & structure | F-reorganization executed | NewCo S corp formed, Keystone LLC contributed, QSub election (Form 8869), EINs, NewCo bank account | P1 - Critical | Medium | Ben | Ben's CPA, tax counsel | 2026-11-16 | 2026-12-15 | 30 | 79 | POST-03 | Y | Not started | bar: 2026-11-16 to 2026-12-14
POST-22 | Documents | Disclosure schedules | Seller schedules against MIPA reps | P1 - Critical | Medium | Ben | Corey | 2026-11-16 | 2026-12-11 | 26 | 75 | POST-15 | Y | Not started | bar: 2026-11-16 to 2026-12-07
POST-23 | Documents | Document turns and negotiation | 2–3 rounds with Ben's counsel on MIPA, Operating Agreement, employment, Services Schedule | P1 - Critical | High | Corey | Jon, Frank, Ben's counsel | 2026-11-16 | 2026-12-11 | 26 | 75 | POST-15, POST-16 | Y | Not started | bar: 2026-11-16 to 2026-12-07
POST-24 | Diligence | Third-party consents | VR Platform, Karbon, PMI, marketplaces, any lease | P2 - High | Medium | Ben | Frank | 2026-11-16 | 2026-12-11 | 26 | 75 | POST-12 | N | Not started | bar: 2026-11-16 to 2026-12-07
POST-25 | Tax & structure | Closing-date 409A and appraisal of Ben's shares; agree Form 8594 allocation | Both sides report the same value | P1 - Critical | Medium | Josh | Appraiser, tax counsel | 2026-11-16 | 2026-12-18 | 33 | 82 | PRE-07 | Y | Not started | bar: 2026-11-16 to 2026-12-14
POST-26 | Integration | Day-1 and 100-day integration plan | Two-segment reporting, monthly close, banking, brand ('Keystone, a Topkey company'), governance calendar | P2 - High | Medium | Frank | Tereno, Jon, Ben | 2026-11-16 | 2026-12-18 | 33 | 82 |  | N | Not started | bar: 2026-11-16 to 2026-12-14
POST-27 | Documents | Escrow agreement and agent | $65K escrow, 15-month term | P3 - Medium | Low | Corey |  | 2026-11-23 | 2026-12-11 | 19 | 75 |  | N | Not started | bar: 2026-11-23 to 2026-12-07
POST-28 | Documents | Securities documents | Subscription, investor questionnaire, Voting Agreement adoption, ROFR/co-sale joinder, IRA stand-off, legends; Form D prep | P2 - High | Low | Corey |  | 2026-12-01 | 2026-12-15 | 15 | 79 |  | N | Not started | Voting Agreement §7.1(b) | bar: 2026-11-30 to 2026-12-14
POST-29 | Governance | Ben option grant | Board approval at 409A strike | P3 - Medium | Low | Corey | Josh | 2026-12-01 | 2026-12-18 | 18 | 82 | POST-25 | N | Not started | bar: 2026-11-30 to 2026-12-14
POST-30 | Integration | Client and team communications plan | Announce after Jan 2; no disruption in 1099 season | P2 - High | Low | Ben | Jon | 2026-12-07 | 2026-12-18 | 12 | 82 |  | N | Not started | bar: 2026-12-07 to 2026-12-14
POST-31 | Closing | Funds-flow memo and wire verification | Escrow $65K on 12/18; $585K to NewCo on first business day; call-back verification | P1 - Critical | Low | Josh | Corey | 2026-12-07 | 2026-12-17 | 11 | 81 |  | N | Not started | bar: 2026-12-07 to 2026-12-14
POST-32 | Closing | Confirm effective time and wire date | Jan 2, 2027 is a Saturday – confirm effective time with tax counsel; wires on Mon Jan 4 | P2 - High | Low | Corey | Tax counsel | 2026-12-01 | 2026-12-11 | 11 | 75 |  | N | Not started | bar: 2026-11-30 to 2026-12-07
POST-33 | Governance | Final board approval and any bring-down consent | Acquisition, share issuance with fair-value finding, employment, option grant, repurchase right | P1 - Critical | Low | Jon | Corey | 2026-12-14 | 2026-12-17 | 4 | 81 | POST-23 | Y | Not started | Charter §4.4.5 | bar: 2026-12-14
POST-34 | Milestone | SIGNING – definitive agreements executed; escrow funded | Target Friday Dec 18, 2026 | P1 - Critical | Medium | Jon | Ben, Corey | 2026-12-18 | 2026-12-18 | 1 | 82 | POST-21, POST-22, POST-23, POST-33 | Y | Not started | bar: 2026-12-14
POST-35 | Closing | Exclusivity window check | 90 days from LOI ≈ Jan 14, 2027; single automatic 30-day extension | P2 - High | Low | Frank |  | 2026-12-18 | 2027-01-14 | 28 | 109 |  | N | Not started | LOI Agreement §1 | bar: 2026-12-14 to 2027-01-11
POST-36 | Milestone | EFFECTIVE DATE – closing | Operating Agreement effective, shares issued, $585K wired Mon Jan 4 | P1 - Critical | Low | Jon | Josh, Corey | 2027-01-02 | 2027-01-04 | 3 | 99 | POST-34 | Y | Not started | bar: 2026-12-28 to 2027-01-04
POST-37 | Post-close | Post-close filings | Form D within 15 days, Pulley cap table, stock notices, blue sky | P2 - High | Low | Corey | Josh | 2027-01-04 | 2027-01-15 | 12 | 110 | POST-36 | N | Not started | bar: 2027-01-04 to 2027-01-11
POST-38 | Post-close | Announcements and client communications | Per POST-30 plan | P2 - High | Low | Ben | Jon | 2027-01-04 | 2027-01-15 | 12 | 110 | POST-36 | N | Not started | bar: 2027-01-04 to 2027-01-11
POST-39 | Post-close | Purchase price allocation and first consolidated close | ASC 805 valuation, NCI, two-segment reporting | P3 - Medium | Medium | Josh |  | 2027-01-04 | 2027-03-31 | 87 | 185 | POST-36 | N | Not started | bar: 2027-01-04 to 2027-03-29
POST-40 | Post-close | First tax distribution; Keystone 1065 and §754 plan | Quarterly tax distribution by Apr 15, 2027 | P3 - Medium | Low | Josh | Tax counsel | 2027-01-04 | 2027-04-15 | 102 | 200 | POST-36 | N | Not started | bar: 2027-01-04 to 2027-04-12
POST-41 | Post-close | Migration cohort 1 readiness review | No client migrations before March (1099 season) | P3 - Medium | Medium | Pete | Darren, Ben | 2027-03-01 | 2027-03-31 | 31 | 185 | POST-18 | N | Not started | bar: 2027-03-01 to 2027-03-29