## Untitled
ID | Workstream | Task | Detail / deliverable | Priority | Difficulty | Owner | Support | Start | Due | Duration (days) | Days to due | Depends on | Critical path | Status | Notes / source | Week of → | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19
PRE-01 | Diligence prep | Request missing Topkey items | Founder Voting Agreement, ROFR & Co-Sale Agreement, current 409A report, Thread documents after Aug 26 maturity, Burkland $60M SAFE, FY2025 audit status, Bryan Beshore's role | P2 - High | Low | Frank | Jon | 2026-09-25 | 2026-09-29 | 5 | 2 |  | N | Not started | Data Room Review §2 / §9 item 9 |  | ■ | ■
PRE-02 | Financing & consents | Confirm Thread Bank line status after Aug 26, 2026 maturity | Extended, paid off or in default? Are monthly compliance certificates and the FY2025 audit current? $500K drawn at 8/31 | P1 - Critical | Low | Jon | Josh | 2026-09-25 | 2026-09-29 | 5 | 2 |  | Y | Not started | LSA §§6.3, 6.8, 7.3, 7.7; Fourth Amendment |  | ■ | ■
PRE-03 | Tax & structure | Engage joint tax counsel (NH experience) | Engagement letter and scope: F-reorg, Rev. Rul. 99-5, NH BPT, QSBS, §83 repurchase wording, Ben's residency, Form 8594, §754. Agree who pays | P1 - Critical | Medium | Jon | Frank, Josh | 2026-09-25 | 2026-10-02 | 8 | 5 |  | Y | Not started | Offer Review v3; Structures report §4 |  | ■ | ■
PRE-04 | Deal terms | Jon decides open terms | Series A options doc (14 decisions) and data-room decisions: Reference Valuation, Thread payoff vs consent, consent strategy, equity-protection fallback, cash timing, disclosure scope, board seat | P1 - Critical | Medium | Jon | Frank | 2026-09-28 | 2026-10-02 | 5 | 5 | PRE-02 | Y | Not started | Options doc v2; Data Room Review §8 |  |  | ■
PRE-05 | Financing & consents | Brief new Felicis partner and a16z (YC ES20 as backup) | Explain partnership, request 55% Requisite Holder consent (§3.3.9, §3.3.8, §3.3.7) and IRA §4.1 ROFO waiver | P1 - Critical | Medium | Jon | Frank | 2026-09-28 | 2026-10-07 | 10 | 10 |  | Y | Not started | Charter Art. IV.B §3.3; IRA §6.6(b) |  |  | ■ | ■
PRE-06 | Financing & consents | Explore insider bridge SAFE ($1–2M) | Felicis/YC bridge signed alongside the deal to restore runway and validate the reference price | P2 - High | High | Jon | Josh | 2026-09-28 | 2026-10-16 | 19 | 19 | PRE-05 | N | Not started | Deal assessment – 'what would improve the odds' |  |  | ■ | ■ | ■
PRE-07 | Tax & structure | Confirm current 409A and engage appraiser | Resolve $0.17 vs $0.22; indicative value of Ben's plain common as of Jan 2, 2027; scope the closing-date update | P1 - Critical | Medium | Josh | Appraiser | 2026-09-28 | 2026-10-09 | 12 | 12 |  | Y | Not started | Data Room Review §3.2 |  |  | ■ | ■
PRE-08 | Diligence prep | Pro forma SAFE-conversion cap table | At $50M and $60M reference; include Thread warrants (up to 42,500 sh) and Ben's shares | P2 - High | Low | Josh | Frank | 2026-09-28 | 2026-10-05 | 8 | 8 |  | N | Not started | Data Room Review §3.1 |  |  | ■ | ■
PRE-09 | Diligence prep | ARR bridge | Investor-update SaaS ARR ($3.06M) to GAAP revenue (Aug run-rate $3.14M all-in / $2.55M platform fees) | P2 - High | Medium | Josh | Frank | 2026-09-28 | 2026-10-07 | 10 | 10 |  | N | Not started | Data Room Review §3.5 |  |  | ■ | ■
PRE-10 | Financing & consents | Fix Kindergarten SAFE cap wording; confirm Burkland SAFE | Correct 'Pre-Money Valuation Cap'; confirm whether the $60M SAFE has closed and falls within the 2025 authorization ($2.5M) | P2 - High | Low | Corey | Josh | 2026-09-28 | 2026-10-07 | 10 | 10 |  | N | Not started | SAFE Summary items 1–2; 2025 consent |  |  | ■ | ■
PRE-11 | Financing & consents | Thread decision and next action | Recommended: request payoff letter (LSA §2.6) and wind-down timeline. Alternative: written consent + §6.10 carve-out for Keystone | P1 - Critical | Medium | Jon | Josh, Corey | 2026-09-29 | 2026-10-09 | 11 | 12 | PRE-02 | Y | Not started | Data Room Review Decision 1 |  |  | ■ | ■
PRE-12 | Seller | Walk-through call with Ben | Verbal offer: 70/30, $650K cash, plain common at reference valuation, preference stack, tax framing, timeline, consents | P1 - Critical | Medium | Jon | Frank | 2026-09-30 | 2026-10-02 | 3 | 5 | PRE-04 | Y | Not started | Jon plans mid-week call |  |  | ■
PRE-13 | Seller | Send Ben tax questions and document request | Offer Review v3 §8 questions; 1120-S, NH-1120/DP-80, 1040 Sch. D/E, S-election acceptance letter | P2 - High | Low | Frank | Tax counsel | 2026-09-30 | 2026-10-02 | 3 | 5 | PRE-03 | N | Not started | Offer Review v3 §8 |  |  | ■
PRE-14 | Tax & structure | Confirm Ben's residency plan | NH vs Europe through 2027 and at exit; drives the whole tax analysis | P1 - Critical | Low | Ben | Tax counsel, Jon | 2026-10-01 | 2026-10-09 | 9 | 12 | PRE-12 | N | Not started | Structures report §4 |  |  | ■ | ■
PRE-15 | Commercial | Amanda / partner bookkeeping firm transition plan | Reconcile Keystone exclusivity with the existing partner firm and Quantum SOW | P2 - High | Medium | Darren | Jon | 2026-09-28 | 2026-10-09 | 12 | 12 |  | N | Not started | Investor update (Bookkeeping) |  |  | ■ | ■
PRE-16 | Governance | Inform co-founder Bryan Beshore | 24.5% FD holder and Key Holder; not required to consent but should hear it from Jon | P3 - Medium | Low | Jon |  | 2026-10-01 | 2026-10-09 | 9 | 12 |  | N | Not started | Voting Agreement §3.2 |  |  | ■ | ■
PRE-17 | Financing & consents | Draft omnibus stockholder consent | Template: 7/1/25 SAFE consent. Covers §3.3.9 non-wholly-owned subsidiary, §3.3.8 related-party arrangements with Ben, §3.3.7 any deferred payment, ROFO waiver, $60M SAFE ratification if needed | P1 - Critical | Medium | Corey | Frank | 2026-10-01 | 2026-10-09 | 9 | 12 | PRE-05 | Y | Not started | Data Room Review §5 |  |  | ■ | ■
PRE-18 | Governance | Confirm board authority | Can a single sitting director approve? Fill the vacant Common Director seat if needed; resolution authorizing LOI | P2 - High | Low | Corey | Jon | 2026-10-01 | 2026-10-09 | 9 | 12 |  | N | Not started | Voting Agreement §1.2; bylaws |  |  | ■ | ■
PRE-19 | Documents | Update LOI v14 and Offer v16 | Apply Jon's decisions and data-room changes (closing conditions, consents, disclosure package, credit-support clause, $50M reference) | P1 - Critical | Low | Frank |  | 2026-10-02 | 2026-10-06 | 5 | 9 | PRE-04 | Y | Not started | Data Room Review §6–7 |  |  | ■ | ■
PRE-20 | Deal terms | Re-run scenario model | 12–15 month runway, $50M reference, 409A range for Ben's closing tax, 15–25% Series A dilution, after-tax rows | P2 - High | Medium | Frank | Josh | 2026-10-02 | 2026-10-08 | 7 | 11 | PRE-07 | N | Not started | Data Room Review §9 item 10 |  |  | ■ | ■
PRE-21 | Documents | Counsel review of LOI v14 / Offer v16 and Exhibit A | Corey sign-off before release; include operating agreement term sheet | P1 - Critical | Medium | Corey | Frank | 2026-10-06 | 2026-10-09 | 4 | 12 | PRE-19 | Y | Not started |  |  |  |  | ■
PRE-22 | Seller | Topkey disclosure package for Ben | Financials through 8/31/26, cap table, charter, SAFE and warrant schedule, Thread summary, ARR bridge; confirm NDA coverage | P2 - High | Medium | Josh | Frank | 2026-10-05 | 2026-10-12 | 8 | 15 | PRE-09 | N | Not started | Data Room Review Decision 6 |  |  |  | ■ | ■
PRE-23 | Documents | Accredited-investor questionnaire ready | Rule 506(b) private placement to Ben | P3 - Medium | Low | Corey |  | 2026-10-05 | 2026-10-12 | 8 | 15 |  | N | Not started |  |  |  |  | ■ | ■
PRE-24 | Financing & consents | Stockholder consent executed (or LOI made conditional) | Felicis + a16z (or YC) signatures; ROFO waiver | P1 - Critical | High | Jon | Felicis, a16z | 2026-10-09 | 2026-10-16 | 8 | 19 | PRE-17 | Y | Not started |  |  |  |  | ■ | ■
PRE-25 | Documents | Send LOI and Offer to Ben | With disclosure package or a date for it | P1 - Critical | Low | Jon | Frank | 2026-10-09 | 2026-10-09 | 1 | 12 | PRE-21 | Y | Not started |  |  |  |  | ■
PRE-26 | Seller | Ben and his advisors review; negotiate LOI | Expect pushback on stock value (409A gap) and cash after tax | P1 - Critical | High | Ben | Jon, Frank | 2026-10-09 | 2026-10-16 | 8 | 19 | PRE-25 | Y | Not started | Deal assessment – concern #3 |  |  |  | ■ | ■
PRE-27 | Milestone | LOI SIGNED | Exclusivity (90 days) starts; target Friday Oct 16 | P1 - Critical | Medium | Jon | Ben | 2026-10-16 | 2026-10-16 | 1 | 19 | PRE-24, PRE-26 | Y | Not started | [5 empty] | ■
Formulas:
Days to due = IF([Status]="Done","",[Due]-TODAY())