## Read Me
Keystone Partnership – Deal Checklist and Timeline
Prepared by AMB Advisory Services LLC for Jon Sukhia / Topkey ¦ September 24, 2026 ¦ Confidential
Targets
LOI signed | Friday, October 16, 2026
Signing and escrow funding | Friday, December 18, 2026
Effective date | Saturday, January 2, 2027 (wires Monday, January 4)
How to use
Status | Edit the Status column on each checklist tab (drop-down). Everything else recalculates.
Dates | Start and Due dates are editable. The Timeline tab and Days to Due update automatically.
Critical path | 'Y' marks tasks that move the Dec 18 signing date if they slip.
Priority
P1 - Critical | On the critical path or a deal-breaker if missed
P2 - High | Needed for signing but has some float
P3 - Medium | Needed but flexible, or post-close
Difficulty
High | Third parties, negotiation or legal complexity; allow extra time
Medium | Several people, some judgment
Low | Straightforward, one owner
People
Jon | Jon Sukhia – Topkey CEO
Frank / Tereno | AMB Advisory
Josh | Burkland – Topkey CFO
Corey | Topkey M&A / securities counsel
Tax counsel | Joint tax counsel with NH experience – to be engaged (PRE-03)
Appraiser | Topkey's 409A appraiser
Pete / Darren | Topkey engineering
Ben | Keystone owner; Ben's counsel and CPA as noted
Sources | LOI v13, Offer v15, Topkey Data Room Review, Series A Decision Options v2, Offer Review v3, deal-call transcripts

## Milestones
Key Milestones and Status
Days remaining count from today.
Milestone | Target date | Days remaining | Linked task | Owner | Gate / what must be true
Thread Bank status confirmed | 2026-09-29 | 4 | PRE-02 | Jon | Know whether the line is extended, repayable or in default
Walk-through call with Ben | 2026-10-02 | 7 | PRE-12 | Jon | Open terms decided (PRE-04)
Tax counsel engaged | 2026-10-02 | 7 | PRE-03 | Jon | Engagement letter signed
LOI v14 / Offer v16 cleared by counsel | 2026-10-09 | 14 | PRE-21 | Corey | Decisions made; consents drafted
LOI sent to Ben | 2026-10-09 | 14 | PRE-25 | Jon | Disclosure package ready or dated
Stockholder consent signed | 2026-10-16 | 21 | PRE-24 | Jon | Felicis + a16z (or YC) = 55% of Preferred
LOI signed | 2026-10-16 | 21 | PRE-27 | Jon | Exclusivity starts (90 days)
Keystone data room complete | 2026-10-30 | 35 | POST-02 | Ben
First drafts: MIPA and Operating Agreement; tax memo | 2026-11-13 | 49 | POST-15 | Corey | Structure confirmed by tax counsel
Diligence substantially complete (QoE) | 2026-11-20 | 56 | POST-09 | Josh | No price-changing findings
Thread paid off and liens released | 2026-11-30 | 66 | POST-05 | Jon | Keystone not a co-borrower
Final agreed documents | 2026-12-11 | 77 | POST-23 | Corey | Schedules and third-party consents in hand
F-reorganization complete | 2026-12-15 | 81 | POST-21 | Ben | NewCo and QSub election in place
Board approval | 2026-12-17 | 83 | POST-33 | Jon | Fair-value finding for shares
SIGNING and escrow funded | 2026-12-18 | 84 | POST-34 | Jon | All P1 pre-signing tasks Done
EFFECTIVE DATE | 2027-01-02 | 99 | POST-36 | Jon | Wires Monday Jan 4
Exclusivity expiry (before extension) | 2027-01-14 | 111 | POST-35 | Frank | Closing must occur first
Status summary
| Pre-LOI | Post-LOI | Total
Not started | 27 | 41 | 68
In progress | 0 | 0 | 0
Done | 0 | 0 | 0
Blocked | 0 | 0 | 0
At risk | 0 | 0 | 0
Total tasks | 27 | 41 | 68
% complete | 0% | 0% | 0%
P1 open (not Done) | 15 | 18 | 33
Overdue (past due, not Done) | 0 | 0 | 0
Formulas:
Days remaining = [Target date]-TODAY()

## Pre-LOI Checklist
Pre-LOI Checklist – Sep 25 to Oct 16, 2026
Edit Status (drop-down), Start and Due. Days to due is blank once Done.
ID | Workstream | Task | Detail / deliverable | Priority | Difficulty | Owner | Support | Start | Due | Duration (days) | Days to due | Depends on | Critical path | Status | Notes / source
PRE-01 | Diligence prep | Request missing Topkey items | Founder Voting Agreement, ROFR & Co-Sale Agreement, current 409A report, Thread documents after Aug 26 maturity, Burkland $60M SAFE, FY2025 audit status, Bryan Beshore's role | P2 - High | Low | Frank | Jon | 2026-09-25 | 2026-09-29 | 5 | 4 |  | N | Not started | Data Room Review §2 / §9 item 9
PRE-02 | Financing & consents | Confirm Thread Bank line status after Aug 26, 2026 maturity | Extended, paid off or in default? Are monthly compliance certificates and the FY2025 audit current? $500K drawn at 8/31 | P1 - Critical | Low | Jon | Josh | 2026-09-25 | 2026-09-29 | 5 | 4 |  | Y | Not started | LSA §§6.3, 6.8, 7.3, 7.7; Fourth Amendment
PRE-03 | Tax & structure | Engage joint tax counsel (NH experience) | Engagement letter and scope: F-reorg, Rev. Rul. 99-5, NH BPT, QSBS, §83 repurchase wording, Ben's residency, Form 8594, §754. Agree who pays | P1 - Critical | Medium | Jon | Frank, Josh | 2026-09-25 | 2026-10-02 | 8 | 7 |  | Y | Not started | Offer Review v3; Structures report §4
PRE-04 | Deal terms | Jon decides open terms | Series A options doc (14 decisions) and data-room decisions: Reference Valuation, Thread payoff vs consent, consent strategy, equity-protection fallback, cash timing, disclosure scope, board seat | P1 - Critical | Medium | Jon | Frank | 2026-09-28 | 2026-10-02 | 5 | 7 | PRE-02 | Y | Not started | Options doc v2; Data Room Review §8
PRE-05 | Financing & consents | Brief new Felicis partner and a16z (YC ES20 as backup) | Explain partnership, request 55% Requisite Holder consent (§3.3.9, §3.3.8, §3.3.7) and IRA §4.1 ROFO waiver | P1 - Critical | Medium | Jon | Frank | 2026-09-28 | 2026-10-07 | 10 | 12 |  | Y | Not started | Charter Art. IV.B §3.3; IRA §6.6(b)
PRE-06 | Financing & consents | Explore insider bridge SAFE ($1–2M) | Felicis/YC bridge signed alongside the deal to restore runway and validate the reference price | P2 - High | High | Jon | Josh | 2026-09-28 | 2026-10-16 | 19 | 21 | PRE-05 | N | Not started | Deal assessment – 'what would improve the odds'
PRE-07 | Tax & structure | Confirm current 409A and engage appraiser | Resolve $0.17 vs $0.22; indicative value of Ben's plain common as of Jan 2, 2027; scope the closing-date update | P1 - Critical | Medium | Josh | Appraiser | 2026-09-28 | 2026-10-09 | 12 | 14 |  | Y | Not started | Data Room Review §3.2
PRE-08 | Diligence prep | Pro forma SAFE-conversion cap table | At $50M and $60M reference; include Thread warrants (up to 42,500 sh) and Ben's shares | P2 - High | Low | Josh | Frank | 2026-09-28 | 2026-10-05 | 8 | 10 |  | N | Not started | Data Room Review §3.1
PRE-09 | Diligence prep | ARR bridge | Investor-update SaaS ARR ($3.06M) to GAAP revenue (Aug run-rate $3.14M all-in / $2.55M platform fees) | P2 - High | Medium | Josh | Frank | 2026-09-28 | 2026-10-07 | 10 | 12 |  | N | Not started | Data Room Review §3.5
PRE-10 | Financing & consents | Fix Kindergarten SAFE cap wording; confirm Burkland SAFE | Correct 'Pre-Money Valuation Cap'; confirm whether the $60M SAFE has closed and falls within the 2025 authorization ($2.5M) | P2 - High | Low | Corey | Josh | 2026-09-28 | 2026-10-07 | 10 | 12 |  | N | Not started | SAFE Summary items 1–2; 2025 consent
PRE-11 | Financing & consents | Thread decision and next action | Recommended: request payoff letter (LSA §2.6) and wind-down timeline. Alternative: written consent + §6.10 carve-out for Keystone | P1 - Critical | Medium | Jon | Josh, Corey | 2026-09-29 | 2026-10-09 | 11 | 14 | PRE-02 | Y | Not started | Data Room Review Decision 1
PRE-12 | Seller | Walk-through call with Ben | Verbal offer: 70/30, $650K cash, plain common at reference valuation, preference stack, tax framing, timeline, consents | P1 - Critical | Medium | Jon | Frank | 2026-09-30 | 2026-10-02 | 3 | 7 | PRE-04 | Y | Not started | Jon plans mid-week call
PRE-13 | Seller | Send Ben tax questions and document request | Offer Review v3 §8 questions; 1120-S, NH-1120/DP-80, 1040 Sch. D/E, S-election acceptance letter | P2 - High | Low | Frank | Tax counsel | 2026-09-30 | 2026-10-02 | 3 | 7 | PRE-03 | N | Not started | Offer Review v3 §8
PRE-14 | Tax & structure | Confirm Ben's residency plan | NH vs Europe through 2027 and at exit; drives the whole tax analysis | P1 - Critical | Low | Ben | Tax counsel, Jon | 2026-10-01 | 2026-10-09 | 9 | 14 | PRE-12 | N | Not started | Structures report §4
PRE-15 | Commercial | Amanda / partner bookkeeping firm transition plan | Reconcile Keystone exclusivity with the existing partner firm and Quantum SOW | P2 - High | Medium | Darren | Jon | 2026-09-28 | 2026-10-09 | 12 | 14 |  | N | Not started | Investor update (Bookkeeping)
PRE-16 | Governance | Inform co-founder Bryan Beshore | 24.5% FD holder and Key Holder; not required to consent but should hear it from Jon | P3 - Medium | Low | Jon |  | 2026-10-01 | 2026-10-09 | 9 | 14 |  | N | Not started | Voting Agreement §3.2
PRE-17 | Financing & consents | Draft omnibus stockholder consent | Template: 7/1/25 SAFE consent. Covers §3.3.9 non-wholly-owned subsidiary, §3.3.8 related-party arrangements with Ben, §3.3.7 any deferred payment, ROFO waiver, $60M SAFE ratification if needed | P1 - Critical | Medium | Corey | Frank | 2026-10-01 | 2026-10-09 | 9 | 14 | PRE-05 | Y | Not started | Data Room Review §5
PRE-18 | Governance | Confirm board authority | Can a single sitting director approve? Fill the vacant Common Director seat if needed; resolution authorizing LOI | P2 - High | Low | Corey | Jon | 2026-10-01 | 2026-10-09 | 9 | 14 |  | N | Not started | Voting Agreement §1.2; bylaws
PRE-19 | Documents | Update LOI v14 and Offer v16 | Apply Jon's decisions and data-room changes (closing conditions, consents, disclosure package, credit-support clause, $50M reference) | P1 - Critical | Low | Frank |  | 2026-10-02 | 2026-10-06 | 5 | 11 | PRE-04 | Y | Not started | Data Room Review §6–7
PRE-20 | Deal terms | Re-run scenario model | 12–15 month runway, $50M reference, 409A range for Ben's closing tax, 15–25% Series A dilution, after-tax rows | P2 - High | Medium | Frank | Josh | 2026-10-02 | 2026-10-08 | 7 | 13 | PRE-07 | N | Not started | Data Room Review §9 item 10
PRE-21 | Documents | Counsel review of LOI v14 / Offer v16 and Exhibit A | Corey sign-off before release; include operating agreement term sheet | P1 - Critical | Medium | Corey | Frank | 2026-10-06 | 2026-10-09 | 4 | 14 | PRE-19 | Y | Not started
PRE-22 | Seller | Topkey disclosure package for Ben | Financials through 8/31/26, cap table, charter, SAFE and warrant schedule, Thread summary, ARR bridge; confirm NDA coverage | P2 - High | Medium | Josh | Frank | 2026-10-05 | 2026-10-12 | 8 | 17 | PRE-09 | N | Not started | Data Room Review Decision 6
PRE-23 | Documents | Accredited-investor questionnaire ready | Rule 506(b) private placement to Ben | P3 - Medium | Low | Corey |  | 2026-10-05 | 2026-10-12 | 8 | 17 |  | N | Not started
PRE-24 | Financing & consents | Stockholder consent executed (or LOI made conditional) | Felicis + a16z (or YC) signatures; ROFO waiver | P1 - Critical | High | Jon | Felicis, a16z | 2026-10-09 | 2026-10-16 | 8 | 21 | PRE-17 | Y | Not started
PRE-25 | Documents | Send LOI and Offer to Ben | With disclosure package or a date for it | P1 - Critical | Low | Jon | Frank | 2026-10-09 | 2026-10-09 | 1 | 14 | PRE-21 | Y | Not started
PRE-26 | Seller | Ben and his advisors review; negotiate LOI | Expect pushback on stock value (409A gap) and cash after tax | P1 - Critical | High | Ben | Jon, Frank | 2026-10-09 | 2026-10-16 | 8 | 21 | PRE-25 | Y | Not started | Deal assessment – concern #3
PRE-27 | Milestone | LOI SIGNED | Exclusivity (90 days) starts; target Friday Oct 16 | P1 - Critical | Medium | Jon | Ben | 2026-10-16 | 2026-10-16 | 1 | 21 | PRE-24, PRE-26 | Y | Not started
Formulas:
Days to due = IF([Status]="Done","",[Due]-TODAY())

## Post-LOI Checklist
Post-LOI Checklist – Oct 19, 2026 to closing (Jan 2, 2027) and post-close
Edit Status (drop-down), Start and Due. Days to due is blank once Done.
ID | Workstream | Task | Detail / deliverable | Priority | Difficulty | Owner | Support | Start | Due | Duration (days) | Days to due | Depends on | Critical path | Status | Notes / source
POST-01 | Project management | Kickoff call, diligence request list, working-group list and calendar | Weekly deal call through signing | P1 - Critical | Low | Frank | Tereno | 2026-10-19 | 2026-10-21 | 3 | 26 | PRE-27 | Y | Not started
POST-02 | Diligence | Keystone target data room populated | Financials, contracts, roster, vendor agreements, IP, tax filings | P1 - Critical | Medium | Ben | Frank | 2026-10-19 | 2026-10-30 | 12 | 35 | POST-01 | Y | Not started
POST-03 | Tax & structure | Tax structure memo | F-reorg, 99-5 treatment, NH BPT, QSBS opinion on Topkey shares, §83 repurchase, Form 8594 allocation, §754, tax distributions | P1 - Critical | High | Tax counsel | Josh, Frank | 2026-10-19 | 2026-11-13 | 26 | 49 | PRE-03 | Y | Not started
POST-04 | Diligence | Entity and tax diligence | Formation docs, S-election acceptance, stock basis/AAA, NH DP-80 apportionment, §174 treatment of Arch/portal | P2 - High | Medium | Tax counsel | Josh | 2026-10-19 | 2026-11-13 | 26 | 49 | POST-02 | N | Not started
POST-05 | Financing & consents | Thread payoff executed | Payoff letter, UCC-3 termination, DACA terminations (Mercury, Brex), warrant status | P1 - Critical | Medium | Jon | Josh, Corey | 2026-10-19 | 2026-11-30 | 43 | 66 | PRE-11 | Y | Not started | LSA §2.6
POST-06 | Financing & consents | Charge-card wind-down and reserve release | Collect $779K receivables, release reserve and operational balances, settle $476K reward-points liability | P2 - High | Medium | Josh | Jon | 2026-10-19 | 2026-12-31 | 74 | 97 | POST-05 | N | Not started | Financials 8/31/26
POST-07 | Financing & consents | Insider bridge SAFE closed (if pursued) | Restores runway before closing cash goes out | P2 - High | High | Jon | Josh, Corey | 2026-10-19 | 2026-12-11 | 54 | 77 | PRE-06 | N | Not started
POST-08 | Diligence | Reverse diligence by Ben's advisors | Q&A on Topkey package, preference stack, runway | P2 - High | Medium | Ben | Josh, Frank | 2026-10-19 | 2026-11-13 | 26 | 49 | PRE-22 | N | Not started
POST-09 | Diligence | Quality of earnings and working-capital peg | Normalized EBITDA ($470–500K), deferred revenue as operating liability, card/revolver balances cleared | P1 - Critical | High | Josh | Frank | 2026-10-26 | 2026-11-20 | 26 | 56 | POST-02 | Y | Not started
POST-10 | Diligence | Client contracts, retention and churn | Revenue per client, properties per client, SMB book sale, departures | P2 - High | Medium | Frank | Tereno | 2026-10-26 | 2026-11-13 | 19 | 49 | POST-02 | N | Not started
POST-11 | Diligence | Offshore team classification and go-forward model | Philippines counsel view; EOR for client leads and accounting staff; special indemnity scope | P1 - Critical | High | Corey | PH counsel, Ben | 2026-10-26 | 2026-11-25 | 31 | 61 | POST-02 | Y | Not started | LOI 7(d); Options doc Decision 8
POST-12 | Diligence | Vendor and software contract assignability | VR Platform, Karbon (through Apr 2027), other tools | P2 - High | Medium | Frank | Corey | 2026-10-26 | 2026-11-13 | 19 | 49 | POST-02 | N | Not started
POST-13 | Diligence | IP assignment confirmation | Arch, client portal, developer work product assigned to Keystone | P2 - High | Medium | Corey | Ben | 2026-10-26 | 2026-11-13 | 19 | 49 | POST-02 | N | Not started
POST-14 | Diligence | Franchise, marketplace and referral agreements | PMI, PMS marketplaces, STR Secrets, commissions | P2 - High | Low | Frank |  | 2026-10-26 | 2026-11-13 | 19 | 49 | POST-02 | N | Not started
POST-15 | Documents | Membership interest purchase agreement – first draft | Reps, indemnity (10% cap, 0.75% basket, 15 months), escrow, set-off, special indemnity, Topkey reps | P1 - Critical | High | Corey | Frank | 2026-10-26 | 2026-11-13 | 19 | 49 | PRE-27 | Y | Not started
POST-16 | Documents | A&R Operating Agreement – first draft | Board, consent rights, tax distributions, ROFR/tag/drag, call (yrs 3–5) and put (yr 5), Formula Price, credit-support limit | P1 - Critical | High | Corey | Frank | 2026-10-26 | 2026-11-13 | 19 | 49 | PRE-27 | Y | Not started | LOI Exhibit A
POST-17 | Documents | Services Schedule | Topkey product pricing, engineering support and IP ownership/licence, referral fee | P1 - Critical | Medium | Frank | Jon, Corey | 2026-11-02 | 2026-11-20 | 19 | 56 | POST-16 | N | Not started | LOI 7(b)
POST-18 | Integration | Migration Protocol | Readiness criteria, cohort sign-off by Ben, Jan–Feb blackout, trust accounts last; tied to trust-accounting general availability | P2 - High | Medium | Pete | Darren, Ben, Frank | 2026-11-02 | 2026-11-25 | 24 | 61 |  | N | Not started
POST-19 | Documents | Ben employment and restrictive-covenant agreements | Title, bonus metrics, severance, Good Reason, non-compete (NH enforceability; Ben abroad) | P1 - Critical | Medium | Corey | Jon | 2026-11-02 | 2026-11-25 | 24 | 61 | PRE-27 | N | Not started
POST-20 | Documents | Related-party recruiting agreement | Arm's-length terms; approved in stockholder consent | P3 - Medium | Low | Corey | Ben | 2026-11-16 | 2026-12-04 | 19 | 70 |  | N | Not started | Charter §3.3.8
POST-21 | Tax & structure | F-reorganization executed | NewCo S corp formed, Keystone LLC contributed, QSub election (Form 8869), EINs, NewCo bank account | P1 - Critical | Medium | Ben | Ben's CPA, tax counsel | 2026-11-16 | 2026-12-15 | 30 | 81 | POST-03 | Y | Not started
POST-22 | Documents | Disclosure schedules | Seller schedules against MIPA reps | P1 - Critical | Medium | Ben | Corey | 2026-11-16 | 2026-12-11 | 26 | 77 | POST-15 | Y | Not started
POST-23 | Documents | Document turns and negotiation | 2–3 rounds with Ben's counsel on MIPA, Operating Agreement, employment, Services Schedule | P1 - Critical | High | Corey | Jon, Frank, Ben's counsel | 2026-11-16 | 2026-12-11 | 26 | 77 | POST-15, POST-16 | Y | Not started
POST-24 | Diligence | Third-party consents | VR Platform, Karbon, PMI, marketplaces, any lease | P2 - High | Medium | Ben | Frank | 2026-11-16 | 2026-12-11 | 26 | 77 | POST-12 | N | Not started
POST-25 | Tax & structure | Closing-date 409A and appraisal of Ben's shares; agree Form 8594 allocation | Both sides report the same value | P1 - Critical | Medium | Josh | Appraiser, tax counsel | 2026-11-16 | 2026-12-18 | 33 | 84 | PRE-07 | Y | Not started
POST-26 | Integration | Day-1 and 100-day integration plan | Two-segment reporting, monthly close, banking, brand ('Keystone, a Topkey company'), governance calendar | P2 - High | Medium | Frank | Tereno, Jon, Ben | 2026-11-16 | 2026-12-18 | 33 | 84 |  | N | Not started
POST-27 | Documents | Escrow agreement and agent | $65K escrow, 15-month term | P3 - Medium | Low | Corey |  | 2026-11-23 | 2026-12-11 | 19 | 77 |  | N | Not started
POST-28 | Documents | Securities documents | Subscription, investor questionnaire, Voting Agreement adoption, ROFR/co-sale joinder, IRA stand-off, legends; Form D prep | P2 - High | Low | Corey |  | 2026-12-01 | 2026-12-15 | 15 | 81 |  | N | Not started | Voting Agreement §7.1(b)
POST-29 | Governance | Ben option grant | Board approval at 409A strike | P3 - Medium | Low | Corey | Josh | 2026-12-01 | 2026-12-18 | 18 | 84 | POST-25 | N | Not started
POST-30 | Integration | Client and team communications plan | Announce after Jan 2; no disruption in 1099 season | P2 - High | Low | Ben | Jon | 2026-12-07 | 2026-12-18 | 12 | 84 |  | N | Not started
POST-31 | Closing | Funds-flow memo and wire verification | Escrow $65K on 12/18; $585K to NewCo on first business day; call-back verification | P1 - Critical | Low | Josh | Corey | 2026-12-07 | 2026-12-17 | 11 | 83 |  | N | Not started
POST-32 | Closing | Confirm effective time and wire date | Jan 2, 2027 is a Saturday – confirm effective time with tax counsel; wires on Mon Jan 4 | P2 - High | Low | Corey | Tax counsel | 2026-12-01 | 2026-12-11 | 11 | 77 |  | N | Not started
POST-33 | Governance | Final board approval and any bring-down consent | Acquisition, share issuance with fair-value finding, employment, option grant, repurchase right | P1 - Critical | Low | Jon | Corey | 2026-12-14 | 2026-12-17 | 4 | 83 | POST-23 | Y | Not started | Charter §4.4.5
POST-34 | Milestone | SIGNING – definitive agreements executed; escrow funded | Target Friday Dec 18, 2026 | P1 - Critical | Medium | Jon | Ben, Corey | 2026-12-18 | 2026-12-18 | 1 | 84 | POST-21, POST-22, POST-23, POST-33 | Y | Not started
POST-35 | Closing | Exclusivity window check | 90 days from LOI ≈ Jan 14, 2027; single automatic 30-day extension | P2 - High | Low | Frank |  | 2026-12-18 | 2027-01-14 | 28 | 111 |  | N | Not started | LOI Agreement §1
POST-36 | Milestone | EFFECTIVE DATE – closing | Operating Agreement effective, shares issued, $585K wired Mon Jan 4 | P1 - Critical | Low | Jon | Josh, Corey | 2027-01-02 | 2027-01-04 | 3 | 101 | POST-34 | Y | Not started
POST-37 | Post-close | Post-close filings | Form D within 15 days, Pulley cap table, stock notices, blue sky | P2 - High | Low | Corey | Josh | 2027-01-04 | 2027-01-15 | 12 | 112 | POST-36 | N | Not started
POST-38 | Post-close | Announcements and client communications | Per POST-30 plan | P2 - High | Low | Ben | Jon | 2027-01-04 | 2027-01-15 | 12 | 112 | POST-36 | N | Not started
POST-39 | Post-close | Purchase price allocation and first consolidated close | ASC 805 valuation, NCI, two-segment reporting | P3 - Medium | Medium | Josh |  | 2027-01-04 | 2027-03-31 | 87 | 187 | POST-36 | N | Not started
POST-40 | Post-close | First tax distribution; Keystone 1065 and §754 plan | Quarterly tax distribution by Apr 15, 2027 | P3 - Medium | Low | Josh | Tax counsel | 2027-01-04 | 2027-04-15 | 102 | 202 | POST-36 | N | Not started
POST-41 | Post-close | Migration cohort 1 readiness review | No client migrations before March (1099 season) | P3 - Medium | Medium | Pete | Darren, Ben | 2027-03-01 | 2027-03-31 | 31 | 187 | POST-18 | N | Not started
Formulas:
Days to due = IF([Status]="Done","",[Due]-TODAY())

## Timeline
Timeline – weekly view (weeks start Monday)
Bars update from the Start and Due dates on the checklist tabs. Red columns: LOI signing (Oct 16), signing (Dec 18), effective date (Jan 2).
ID | Task | Owner | Priority | Start | Due | Status | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12
PRE-LOI
PRE-01 | Request missing Topkey items | Frank | P2 - High | 2026-09-25 | 2026-09-29 | Not started | ■ | ■
PRE-02 | Confirm Thread Bank line status after Aug 26, 2026 maturity | Jon | P1 - Critical | 2026-09-25 | 2026-09-29 | Not started | ■ | ■
PRE-03 | Engage joint tax counsel (NH experience) | Jon | P1 - Critical | 2026-09-25 | 2026-10-02 | Not started | ■ | ■
PRE-04 | Jon decides open terms | Jon | P1 - Critical | 2026-09-28 | 2026-10-02 | Not started |  | ■
PRE-05 | Brief new Felicis partner and a16z (YC ES20 as backup) | Jon | P1 - Critical | 2026-09-28 | 2026-10-07 | Not started |  | ■ | ■
PRE-06 | Explore insider bridge SAFE ($1–2M) | Jon | P2 - High | 2026-09-28 | 2026-10-16 | Not started |  | ■ | ■ | ■
PRE-07 | Confirm current 409A and engage appraiser | Josh | P1 - Critical | 2026-09-28 | 2026-10-09 | Not started |  | ■ | ■
PRE-08 | Pro forma SAFE-conversion cap table | Josh | P2 - High | 2026-09-28 | 2026-10-05 | Not started |  | ■ | ■
PRE-09 | ARR bridge | Josh | P2 - High | 2026-09-28 | 2026-10-07 | Not started |  | ■ | ■
PRE-10 | Fix Kindergarten SAFE cap wording; confirm Burkland SAFE | Corey | P2 - High | 2026-09-28 | 2026-10-07 | Not started |  | ■ | ■
PRE-11 | Thread decision and next action | Jon | P1 - Critical | 2026-09-29 | 2026-10-09 | Not started |  | ■ | ■
PRE-12 | Walk-through call with Ben | Jon | P1 - Critical | 2026-09-30 | 2026-10-02 | Not started |  | ■
PRE-13 | Send Ben tax questions and document request | Frank | P2 - High | 2026-09-30 | 2026-10-02 | Not started |  | ■
PRE-14 | Confirm Ben's residency plan | Ben | P1 - Critical | 2026-10-01 | 2026-10-09 | Not started |  | ■ | ■
PRE-15 | Amanda / partner bookkeeping firm transition plan | Darren | P2 - High | 2026-09-28 | 2026-10-09 | Not started |  | ■ | ■
PRE-16 | Inform co-founder Bryan Beshore | Jon | P3 - Medium | 2026-10-01 | 2026-10-09 | Not started |  | ■ | ■
PRE-17 | Draft omnibus stockholder consent | Corey | P1 - Critical | 2026-10-01 | 2026-10-09 | Not started |  | ■ | ■
PRE-18 | Confirm board authority | Corey | P2 - High | 2026-10-01 | 2026-10-09 | Not started |  | ■ | ■
PRE-19 | Update LOI v14 and Offer v16 | Frank | P1 - Critical | 2026-10-02 | 2026-10-06 | Not started |  | ■ | ■
PRE-20 | Re-run scenario model | Frank | P2 - High | 2026-10-02 | 2026-10-08 | Not started |  | ■ | ■
PRE-21 | Counsel review of LOI v14 / Offer v16 and Exhibit A | Corey | P1 - Critical | 2026-10-06 | 2026-10-09 | Not started |  |  | ■
PRE-22 | Topkey disclosure package for Ben | Josh | P2 - High | 2026-10-05 | 2026-10-12 | Not started |  |  | ■ | ■
PRE-23 | Accredited-investor questionnaire ready | Corey | P3 - Medium | 2026-10-05 | 2026-10-12 | Not started |  |  | ■ | ■
PRE-24 | Stockholder consent executed (or LOI made conditional) | Jon | P1 - Critical | 2026-10-09 | 2026-10-16 | Not started |  |  | ■ | ■
PRE-25 | Send LOI and Offer to Ben | Jon | P1 - Critical | 2026-10-09 | 2026-10-09 | Not started |  |  | ◆
PRE-26 | Ben and his advisors review; negotiate LOI | Ben | P1 - Critical | 2026-10-09 | 2026-10-16 | Not started |  |  | ■ | ■
PRE-27 | LOI SIGNED | Jon | P1 - Critical | 2026-10-16 | 2026-10-16 | Not started |  |  |  | ◆
POST-LOI
POST-01 | Kickoff call, diligence request list, working-group list and calendar | Frank | P1 - Critical | 2026-10-19 | 2026-10-21 | Not started |  |  |  |  | ■
POST-02 | Keystone target data room populated | Ben | P1 - Critical | 2026-10-19 | 2026-10-30 | Not started |  |  |  |  | ■ | ■
POST-03 | Tax structure memo | Tax counsel | P1 - Critical | 2026-10-19 | 2026-11-13 | Not started |  |  |  |  | ■ | ■ | ■ | ■
POST-04 | Entity and tax diligence | Tax counsel | P2 - High | 2026-10-19 | 2026-11-13 | Not started |  |  |  |  | ■ | ■ | ■ | ■
POST-05 | Thread payoff executed | Jon | P1 - Critical | 2026-10-19 | 2026-11-30 | Not started |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■
POST-06 | Charge-card wind-down and reserve release | Josh | P2 - High | 2026-10-19 | 2026-12-31 | Not started |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
POST-07 | Insider bridge SAFE closed (if pursued) | Jon | P2 - High | 2026-10-19 | 2026-12-11 | Not started |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
POST-08 | Reverse diligence by Ben's advisors | Ben | P2 - High | 2026-10-19 | 2026-11-13 | Not started |  |  |  |  | ■ | ■ | ■ | ■
POST-09 | Quality of earnings and working-capital peg | Josh | P1 - Critical | 2026-10-26 | 2026-11-20 | Not started | [5 empty] | ■ | ■ | ■ | ■
POST-10 | Client contracts, retention and churn | Frank | P2 - High | 2026-10-26 | 2026-11-13 | Not started | [5 empty] | ■ | ■ | ■
POST-11 | Offshore team classification and go-forward model | Corey | P1 - Critical | 2026-10-26 | 2026-11-25 | Not started | [5 empty] | ■ | ■ | ■ | ■ | ■
POST-12 | Vendor and software contract assignability | Frank | P2 - High | 2026-10-26 | 2026-11-13 | Not started | [5 empty] | ■ | ■ | ■
POST-13 | IP assignment confirmation | Corey | P2 - High | 2026-10-26 | 2026-11-13 | Not started | [5 empty] | ■ | ■ | ■
POST-14 | Franchise, marketplace and referral agreements | Frank | P2 - High | 2026-10-26 | 2026-11-13 | Not started | [5 empty] | ■ | ■ | ■
POST-15 | Membership interest purchase agreement – first draft | Corey | P1 - Critical | 2026-10-26 | 2026-11-13 | Not started | [5 empty] | ■ | ■ | ■
POST-16 | A&R Operating Agreement – first draft | Corey | P1 - Critical | 2026-10-26 | 2026-11-13 | Not started | [5 empty] | ■ | ■ | ■
POST-17 | Services Schedule | Frank | P1 - Critical | 2026-11-02 | 2026-11-20 | Not started | [6 empty] | ■ | ■ | ■
POST-18 | Migration Protocol | Pete | P2 - High | 2026-11-02 | 2026-11-25 | Not started | [6 empty] | ■ | ■ | ■ | ■
POST-19 | Ben employment and restrictive-covenant agreements | Corey | P1 - Critical | 2026-11-02 | 2026-11-25 | Not started | [6 empty] | ■ | ■ | ■ | ■
POST-20 | Related-party recruiting agreement | Corey | P3 - Medium | 2026-11-16 | 2026-12-04 | Not started | [8 empty] | ■ | ■ | ■
POST-21 | F-reorganization executed | Ben | P1 - Critical | 2026-11-16 | 2026-12-15 | Not started | [8 empty] | ■ | ■ | ■ | ■ | ■
POST-22 | Disclosure schedules | Ben | P1 - Critical | 2026-11-16 | 2026-12-11 | Not started | [8 empty] | ■ | ■ | ■ | ■
POST-23 | Document turns and negotiation | Corey | P1 - Critical | 2026-11-16 | 2026-12-11 | Not started | [8 empty] | ■ | ■ | ■ | ■
POST-24 | Third-party consents | Ben | P2 - High | 2026-11-16 | 2026-12-11 | Not started | [8 empty] | ■ | ■ | ■ | ■
POST-25 | Closing-date 409A and appraisal of Ben's shares; agree Form 8594 allocation | Josh | P1 - Critical | 2026-11-16 | 2026-12-18 | Not started | [8 empty] | ■ | ■ | ■ | ■ | ■
POST-26 | Day-1 and 100-day integration plan | Frank | P2 - High | 2026-11-16 | 2026-12-18 | Not started | [8 empty] | ■ | ■ | ■ | ■ | ■
POST-27 | Escrow agreement and agent | Corey | P3 - Medium | 2026-11-23 | 2026-12-11 | Not started | [9 empty] | ■ | ■ | ■
POST-28 | Securities documents | Corey | P2 - High | 2026-12-01 | 2026-12-15 | Not started | [10 empty] | ■ | ■ | ■
POST-29 | Ben option grant | Corey | P3 - Medium | 2026-12-01 | 2026-12-18 | Not started | [10 empty] | ■ | ■ | ■
POST-30 | Client and team communications plan | Ben | P2 - High | 2026-12-07 | 2026-12-18 | Not started | [11 empty] | ■ | ■
POST-31 | Funds-flow memo and wire verification | Josh | P1 - Critical | 2026-12-07 | 2026-12-17 | Not started | [11 empty] | ■ | ■
POST-32 | Confirm effective time and wire date | Corey | P2 - High | 2026-12-01 | 2026-12-11 | Not started | [10 empty] | ■ | ■
POST-33 | Final board approval and any bring-down consent | Jon | P1 - Critical | 2026-12-14 | 2026-12-17 | Not started | [12 empty] | ■
POST-34 | SIGNING – definitive agreements executed; escrow funded | Jon | P1 - Critical | 2026-12-18 | 2026-12-18 | Not started | [12 empty] | ◆
POST-35 | Exclusivity window check | Frank | P2 - High | 2026-12-18 | 2027-01-14 | Not started | [12 empty] | ■ | ■ | ■ | ■ | ■
POST-36 | EFFECTIVE DATE – closing | Jon | P1 - Critical | 2027-01-02 | 2027-01-04 | Not started | [14 empty] | ■ | ■
POST-37 | Post-close filings | Corey | P2 - High | 2027-01-04 | 2027-01-15 | Not started | [15 empty] | ■ | ■
POST-38 | Announcements and client communications | Ben | P2 - High | 2027-01-04 | 2027-01-15 | Not started | [15 empty] | ■ | ■
POST-39 | Purchase price allocation and first consolidated close | Josh | P3 - Medium | 2027-01-04 | 2027-03-31 | Not started | [15 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
POST-40 | First tax distribution; Keystone 1065 and §754 plan | Josh | P3 - Medium | 2027-01-04 | 2027-04-15 | Not started | [15 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
POST-41 | Migration cohort 1 readiness review | Pete | P3 - Medium | 2027-03-01 | 2027-03-31 | Not started | [23 empty] | ■ | ■ | ■ | ■ | ■